## Sheet1
SARIM SHAHAWR- 501109286
Risk Management and Analysis
Risk | Description
Integration Complexity (Technical Risk): #1 | Integrating the new system with existing inventory and order management systems of suppliers could be more complex than anticipated, leading to potential delays and increased development time.
Data Security Breaches (Technical and Business Risk): #2 | Given the system's handling of sensitive customer and supplier data, there is a risk of security breaches, which could compromise data integrity and result in loss of trust and potential legal implications.
Scalability Challenges (Technical Risk): #3 | As the business grows, the system may struggle to handle increased loads, affecting performance during peak hours and potentially leading to customer dissatisfaction.
Supplier Collaboration Difficulties (Business Risk): #4 | Ensuring all suppliers adapt to and integrate with the new system could be challenging, potentially leading to inventory discrepancies and order management issues.
User Adoption (Business Risk):#5 | There's a risk that the system's user interface may not meet customer expectations or be as intuitive as planned, leading to lower user adoption rates.
Regulatory Compliance (Legal and Business Risk):#6 | Failure to comply with new or existing regulations related to online transactions and data protection can lead to fines and necessitate costly system modifications.
Project Overruns (Economical Risk):#7 | Misestimations of time and resources needed for the project could lead to budget overruns and extended timelines.
Technical Debt (Technical Risk):#8 | In the rush to deliver, the project might accumulate technical debt, leading to future costs and delays in system maintenance and updates.
Change Management Issues (Business Risk):#9 | Employee resistance to new processes and systems could hinder effective implementation and usage of the new system.
The Monte Carlo Simulation Results (100 Simulations)
|  | Risk | Risk Probability | Expected Impacts | Expected Risk Factor | Risk Factor Rating | High-Risk Factors
|  | Integration Complexity | 50.7% | 2.38 (Marginal to Critical) | 1.21 | #6/7
|  | Data Security Breaches | 51.3% | 2.61 (Critical) | 1.34 | #2/3 | High-Risk Factor #2
|  | Scalability Challenges | 46.3% | 2.49 (Marginal to Critical) | 1.15 | #8
|  | Supplier Collaboration Difficulties | 47.5% | 2.55 (Critical) | 1.21 | #6/7
|  | User Adoption | 52.8% | 2.53 (Marginal to Critical) | 1.34 | #2/3
|  | Regulatory Compliance | 53.1% | 2.57 (Critical) | 1.36 | #1 | High-Risk Factor #1
|  | Project Overruns | 47.5% | 2.39 (Marginal to Critical) | 1.13 | #9
|  | Technical Debt | 47.8% | 2.66 (Critical) | 1.27 | #5
|  | Change Management Issues | 51.8% | 2.52 (Marginal to Critical) | 1.31 | #4 | High-Risk Factor #3
Side note: Since some of the Expected risk factors are the same, I had put 2 to show they can be either rank
Impact on Project Objectives:
1. Cost: Risk #1,3,7,8 directly impact and increases project costs owing to the requirement for additional resources, potential fines, and the expense of dealing with technical debt and scalability difficulties.
2. Time: Risk # 1,4,7,8 might cause project delays by prolonging the duration required for integration complexity, supplier coordination, and addressing technical debt.
3. Scope: Risk # 2,4,6,9 could cause change to include extra security features, complzance measures, and change management procedures.
4. Quality: Risk # 2,3,5,8 affects the project's quality, ranging from system performance and user happiness to long-term system maintainability and dependability.
The probabilities Scale:
Highly unlikely (p < 20%)
Unlikely (20% < p < 40%)
About even (40% < p < 60%)
Likely (60% < p < 80%)
Highly likely (p > 80%)
The impacts are rated as:
1: Negligible
2: Marginal
3: Critical
4: Catastrophic